## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Concept Development Phase | 1 | 4 | 1 | 4 | 100%
Analyze Customer Requirements | 1 | 0.5
Develop Use Cases | 1 | 2
Develop Conceptual Structure | 2 | 2
Derive System Technical Requirements | 3 | 2
Prepare Data for SRR Presentation | 3 | 2
Conduct SRR | 0 | 0 | bar: PERIODS 4
Preliminary Design Phase | 5 | 5 | 5 | 5 | 100%
Define Logical Structure (BDDs) | 5 | 2
Define System Key Parameters and TPMs | 5 | 2
Define Logical Behavior (Activity, State) | 6 | 2
Define Logical Interfacy Types | 7 | 2
Develop Subsystem IBDs | 7 | 3
Peform Parametric Analysis | 8 | 2
Develop Subsystem Specifications | 8 | 2
Prepare Data for PDR Presentation | 9 | 1
Conduct PDR | 0 | 0
Detailed Design Phase | 10 | 5 | 10 | 5 | 100%
Define Pump SS Phsycal Structure | 10 | 3
Define Pipe SS Physical Structure | 10 | 3
Define Monitor and Control SS Physical Structure | 10 | 3
Update Key Parameter Values and TPMs | 13 | 1
Prepare Data for CDR Presentation | 14 | 1
Condiuct CDR